## OVERALL
PAMANA DILG FUND (Region XIII)
PROJECT PROGRESS REPORT
PROJECT YEAR: 2012 |  | UPDATE AS OF : | 2014-08-05 13:57
PROVINCE | ALLOCATION | ACCOMPLISHMENT | PERCENTAGE OF ACCOMPLISHMENT | WEIGHT
AGUSAN DEL NORTE | 20000000 | 19465600 | 97.33% | 12.32%
AGUSAN DEL SUR | 70000000 | 62739500 | 89.63% | 39.71%
SURIGAO DEL NORTE | 30000000 | 12775050 | 42.58% | 8.085%
SURIGAO DEL SUR | 38000000 | 37600000 | 98.95% | 23.8%
TOTAL | 158000000 | 132580150 |  | 83.91%
PROJECT YEAR: 2013 |  | UPDATE AS OF : | 2014-08-05 13:57
PROVINCE | ALLOCATION | ACCOMPLISHMENT | PERCENTAGE OF ACCOMPLISHMENT | WEIGHT
AGUSAN DEL NORTE | 5000000 | 0 | 0% | 0%
SURIGAO DEL NORTE | 135000000 | 63369500 | 46.94% | 28.38%
SURIGAO DEL SUR | 83300000 | 30123200 | 32.56% | 13.49%
TOTAL | 223300000 | 93492700 |  | 41.87%
Accomplishment per Province
Accomplishment of the Region

## AGUSAN DEL NORTE
PAMANA DILG FUND (Region XIII)
PROGRESS AND ACCOMPLISHMENT
PROVINCE: AGUSAN DEL NORTE | [6 empty] | UPDATE AS OF: | 2014-08-05 13:57
PROJECT PROFILE |  |  |  | PRE-CONSTRUCTION STAGE |  |  | CONSTRUCTION STAGE | POST - CONSTRUCTION STAGE |  |  |  | REMARKS
NO | PROJECT | LOCATION (MUNICIPALITY) | ALLOCATION | PREPARATION OF PROPOSAL | RELEASED OF FIRST TRANCHE | PROCUREMENT | IMPLEMENTATION | REQUEST FOR 2ND TRANCHE | RELEASE OF 2ND TRANCHE | FINANCIALLY LIQUIDATED | PROJECT INAGURATED
PROJECT YEAR: 2012
1 | Rehabilitation of Bangonay-NRJ-Inayao-Palo 12 Farm to Market Road | Jabonga | 2000000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 2000000 | 10% | 100%
2 | Concreting of San Isidro Farm to Market Road | Las Nieves | 1500000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 1500000 | 7.5% | 100%
3 | Concreting of E.G. Montilla Farm to Market Road | Las Nieves | 500000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 500000 | 2.5% | 100%
4 | Concreting Taod-oy Farm to Market Road | Magallanes | 1800000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 1800000 | 9% | 100%
5 | Installation of Potable Water Supply System Level II at Barangay Taod-oy | Magallanes | 200000 | ü | ü | ü | 100% | [5 empty] | 200000 | 1% | 100%
6 | Repair/Rehabilitation of River Flood Control (Armoc Rock Filling) | Tubay | 2000000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 2000000 | 10% | 100%
7 | Construction of Abilan Farm to Market Road | Buenavista | 2000000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 2000000 | 10% | 100%
8 | Rehabilitation of Manoligao-Liongan Farm to Market Road, Phase 1 | Carmen | 1000000 | ü | ü | ü | 100% |  |  |  |  | Completed subject to COA inspection. | 1000000 | 5% | 100%
9 | Rehabilitation of Poblacion-Sisiman Farm to Market Road | Carmen | 1000000 | ü | ü | ü | 100% | ü | ü |  |  |  | 1000000 | 5% | 100%
10 | Upgrading of Bangayan-Zapanta Valley Farm to Market Road | Kitcharao | 2000000 | ü | ü | ü | 100% | ü | ü |  |  |  | 2000000 | 10% | 100%
11 | Concreting of Jaguimitan Farm to Market Road | Nasipit | 2000000 | ü | ü | ü | 100% |  |  |  |  | Completed subject to COA inspection. | 2000000 | 10% | 100%
12 | Construction of Tagbongabong-Kanluran-San Antonio FMR | RTR | 2000000 | ü | ü | ü | 73.28% |  |  |  |  | On-going | 1465600 | 7.328% | 73.28%
13 | Construction of Pob 1-Pangaylan IP-Mantingue Farm to Mantigue | Santiago | 2000000 | ü | ü | ü | 100% | ü | ü |  |  | Project completed. Second Tranche released. | 2000000 | 10% | 100%
| TOTAL |  | 20000000 | TOTAL ACCOMPLISHMENT: |  |  | 97.33% | [5 empty] | 19465600 | 97.33%
PROJECT YEAR: 2013
1 | Construction of Cabadbaran-Putting Bato-Lanuza Road (Phase 1) | Cabadbaran | 5000000 | ü | ü | ü | [5 empty] | On-going but no report yet submitted |  |  | 0
| TOTAL |  | 5000000 | TOTAL ACCOMPLISHMENT: |  |  | 0%
ON-GOING
COMPLETED
SUSPENDED

## AGUSAN DEL SUR
PAMANA DILG FUND (Region XIII)
PROGRESS AND ACCOMPLISHMENT
PROVINCE: AGUSAN DEL SUR | [6 empty] | UPDATE AS OF: | 2014-08-05 13:57
PROJECT PROFILE |  |  |  | PRE-CONSTRUCTION STAGE |  |  | CONSTRUCTION STAGE | POST - CONSTRUCTION STAGE |  |  |  | REMARKS
NO | PROJECT | LOCATION (MUNICIPALITY) | ALLOCATION | PREPARATION OF PROPOSAL | RELEASED OF FIRST TRANCHE | PROCUREMENT | IMPLEMENTATION | REQUEST FOR 2ND TRANCHE | RELEASE OF 2ND TRANCHE | FINANCIALLY LIQUIDATED | PROJECT INAGURATED
PROJECT YEAR: 2012
1 | Rehabilitation of NRJ San Juan-New Tubigon-San Roque Road | Sibagat | 10000000 | ü | ü | ü | 30.37% |  |  |  |  | On-going. New expiry date is November 22, 2013 | 3037000 | 4.339% | 30.37%
2 | Rehabilitation of La Purisima-Sitio Gacub Road | Prosperidad | 10000000 | ü | ü | ü | 100% |  |  |  |  | Completed. For COA inspection | 10000000 | 14.29% | 100%
3 | Rehabilitation of Tapaz-Tagumpay-Guinobatan Road | Sta. Josefa | 25000000 | ü | ü | ü | 98.81% |  |  |  |  | First variation completed. Work for second variation is on-going | 24702500 | 35.29% | 98.81%
4 | Rehabilitation of Katipunan-Limot-Sisimon-Anitap Road | Veruela | 25000000 | ü | ü | ü | 100% |  |  |  |  | Completed but there is a recommendation for variation order. | 25000000 | 35.71% | 100%
| TOTAL |  | 70000000 | TOTAL ACCOMPLISHMENT: |  |  | 89.63% | [5 empty] | 62739500 | 89.63%
ON-GOING
COMPLETED
SUSPENDED

## SURIGAO DEL NORTE
PAMANA DILG FUND (Region XIII)
PROGRESS AND ACCOMPLISHMENT
PROVINCE: SURIGAO DEL NORTE | [6 empty] | UPDATE AS OF: | 2014-08-05 13:57
PROJECT PROFILE |  |  |  | PRE-CONSTRUCTION STAGE |  |  | CONSTRUCTION STAGE | POST - CONSTRUCTION STAGE |  |  |  | REMARKS
NO | PROJECT | LOCATION (MUNICIPALITY) | ALLOCATION | PREPARATION OF PROPOSAL | RELEASED OF FIRST TRANCHE | PROCUREMENT | IMPLEMENTATION | REQUEST FOR 2ND TRANCHE | RELEASE OF 2ND TRANCHE | FINANCIALLY LIQUIDATED | PROJECT INAGURATED
PROJECT YEAR: 2012
1 | Rehabilitation of Mainit-Matin-ao-Binga-Paco Road Phase 1 | Mainit | 5000000 | ü | ü | ü | 88.5% |  |  |  |  | On-going | 4425000 | 14.75% | 88.5%
2 | Rehabilitation of Ombong-Camp Edward FMR | Alegria | 4000000 | ü | ü | ü | 100% |  |  |  |  | Completed, subject to COA inspection | 4000000 | 13.33% | 100%
3 | Construction of Water System at Barangay Villariza | Malimono | 500000 | ü | ü |  | 0% |  |  |  |  | First bidding has failed. DILG to communicate with LGU to fast-track the implementation and do catch-up plan.Closely monitor the project. Alert mechanism to be applied. | 0 | 0% | 0%
4 | Construction of Water System at Barangay Can-aga | Malimono | 1000000 | ü | ü |  | 0% | [5 empty] | 0 | 0% | 0%
5 | Construction of Water System at Barangay Masgad | Malimono | 3000000 | ü | ü |  | 0% | [5 empty] | 0 | 0% | 0%
6 | Construction of FMR in Pili-Karihatag (Phase 1) | Malimono | 5000000 | ü | ü | ü | 44.53% |  |  |  |  | On-going | 2226500 | 7.422% | 44.53%
7 | Abaca Development at Barangay Ferlda | Alegria | 1000000 | ü | ü |  | 0% |  |  |  |  | Still finalizing the procurment stage. DILG to communicate with LGU to fast-track the implementation and do catch-up plan. Alert mechanism to be applied | 0 | 0% | 0%
8 | Rehabilitation of FMR at Sitio Pinaypayan-Brazil, Barangay Mat-i | Surigao City | 4500000 | ü | ü | ü | 47.19% |  |  |  |  | On-going | 2123550 | 7.079% | 47.19%
9 | Livelihood Program in Barangay Mat-I, Surigao City | Surigao City | 500000 | ü | ü |  | 0% |  |  |  |  | On-going. No report yet submitted | 0 | 0% | 0%
10 | Integrated High Value Crops Production and Mangrove Protection with Livelihood | Siargao Islands | 5500000 | ü | ü |  | 0% |  |  |  |  | On-going. Revised report to be submitted | 0 | 0% | 0%
| TOTAL |  | 30000000 | TOTAL ACCOMPLISHMENT: |  |  | 42.58% | [5 empty] | 12775050 | 42.58%
PROJECT YEAR: 2013
1 | Construction of Campo-Little Baguio Road, Bacuag (7km) | Bacuag | 30000000 | ü | ü | ü | 86.08% |  |  |  |  | On-going | 25824000 | 19.13% | 86.08%
2 | Rehabilitation of Pili-Karihatag Road, (Phase 2), Malimono (2.38km) | Malimono | 15000000 | ü | ü | ü | 56.56% |  |  |  |  | On-going | 8484000 | 6.284% | 56.56%
3 | Rehabilitation of Pinaypayan-Brazil Road, Mat-I Surigao City (0.96km) | Surigao City | 10000000 | ü | ü | ü | 28.05% |  |  |  |  | On-going | 2805000 | 2.078% | #REF!
4 | Rehabilitation of Cantapoy-Villariza, Malimono (1.22km) | Malimono | 10000000 | ü | ü | ü | 25% |  |  |  |  | On-going | 2500000 | 1.852% | 25%
5 | Rehabilitation of Diaz-Magtangale, San Francisco (3.19km) | San Francisco | 15000000 | ü | ü | ü | 68.51% |  |  |  |  | On-going | 10276500 | 7.612% | #REF!
6 | Construction of 50 meter Bailey Bridge at Cantugas, Mainit (50m) | Mainit | 15000000 | ü | ü | ü | 71.2% |  |  |  |  | On-going | 10680000 | 7.911% | 71.2%
7 | Construction of Banban-Taganaan-Magsaysay, Placer Road (1.7km) | Tagana-an and Placer | 10000000 | ü | ü | ü | 28% |  |  |  |  | On-going | 2800000 | 2.074% | #REF!
8 | Rehabilitation of Antipolo-Tuburan-Quezon, Del Carmen (8.93km) | Del Carmen | 30000000 | ü | ü | ü | [5 empty] | On-going. No report yet submitted | 0 | 0% | 0%
| TOTAL |  | 135000000 | TOTAL ACCOMPLISHMENT: |  |  | 46.94% | [5 empty] | 63369500 | 46.94%
ON-GOING
COMPLETED
SUSPENDED

## SURIGAO DEL SUR
PAMANA DILG FUND (Region XIII)
PROGRESS AND ACCOMPLISHMENT
PROVINCE: SURIGAO DEL SUR | [6 empty] | UPDATE AS OF: | [9 empty] | 2014-08-05 13:57
PROJECT PROFILE |  |  |  | PRE-CONSTRUCTION STAGE |  |  | CONSTRUCTION STAGE | [9 empty] | POST - CONSTRUCTION STAGE |  |  |  | REMARKS
NO | PROJECT | LOCATION (MUNICIPALITY) | ALLOCATION | PREPARATION OF PROPOSAL | RELEASED OF FIRST TRANCHE | PROCUREMENT | IMPLEMENTATION | [9 empty] | REQUEST FOR 2ND TRANCHE | RELEASE OF 2ND TRANCHE | FINANCIALLY LIQUIDATED | PROJECT INAGURATED
PROJECT YEAR: 2012
1 | Rehabilitation and Repair of Poblacion-Magsaysay-Osmena-Villaverde FMR | Tagbina | 13500000 | ü | ü | ü | 100% | [9 empty] | ü | ü |  | ü | Project completed and second tranche released | 13500000 | 35.53% | 100%
2 | Rehabilitation and Repair of Manlambing-Carpenito-Kahayagan FMR | Tagbina | 9000000 | ü | ü | ü | 100% | [9 empty] | ü | ü | ü | ü | Project complete and financially liquidated | 9000000 | 23.68% | 100%
3 | Rehabilitation and Repair of San Isidro-Maticdum-Mabuhay FMR | Tandag | 6500000 | ü | ü | ü | 100% | [9 empty] | ü | ü | ü | ü | Project complete and financially liquidated | 6500000 | 17.11% | 100%
4 | Installation of Potable Water System Level II at Barangay Maligaya | Hinatuan | 3000000 | ü | ü | ü | 100% | [9 empty] | ü | ü |  |  | Project completed and second tranche released | 3000000 | 7.895% | 100%
5 | Installation of Potable Water System Level II at Barangay San Antonio | Bislig City | 2500000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Request for 2nd tranche submitted but documentary requirements still incomplete | 2500000 | 6.579% | 100%
6 | Rubber Based Production System at Barangay San Pedro (Livelihood) | Marihatag | 2000000 | ü | ü | ü | 89% | [13 empty] | On-going | 1780000 | 4.684% | 89%
7 | Rubber Based Production System at Barangay Panaosawon (Livelihood) | Bayabas | 1200000 | ü | ü | ü | 90% | [13 empty] | On-going | 1080000 | 2.842% | 90%
8 | Value Adding Activities for Abaca Weaving Project at Brgy. Pong-on and Janipaan | San Agustin | 300000 | ü | ü | ü | 80% | [9 empty] | ü |  |  |  | Completed on the first tranche only. | 240000 | 0.6316% | 80%
| TOTAL |  | 38000000 | TOTAL ACCOMPLISHMENT: |  |  | 98.95% | [14 empty] | 37600000 | 98.95%
PROJECT YEAR: 2013
1 | Rehabilitation of Sitio Sote, Burboanan to Junction Mabug, San Roque Road (6km) | Bislig City | 2500000 | ü | ü | ü | 100% | [9 empty] | ü | ü |  |  | Completed | 2500000 | 3.001% | 100%
2 | Concreting of Maticdum-Mabuhay Road, Maticdum, Tandag City | Tandag City | 20000000 | ü | ü |  | 0% | [13 empty] | Procurement stage | 0 | 0% | 0%
3 | Rehabilitation of Mabahin Spring Development, 7km | Cortes | 3000000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Completed | 3000000 | 3.601% | 100%
| Rehabilitation of Matho Spring Development 5km |  | 3000000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Completed | 3000000 | 3.601% | 100%
| Rehabilitation of Tigao Spring Development 4km |  | 3000000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Completed | 3000000 | 3.601% | 100%
| Rehabitation of Manlico to Poblacion, 10 km |  | 3000000 | ü | ü | ü | 77.44% | [13 empty] | On-going | 2323200 | 2.789% | 77.44%
| Rehabilitation of Burgos Spring Development |  | 3000000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Completed | 3000000
4 | Construction of Water System Level I (Boac na Bato) | Cortes | 300000 | ü | ü | ü | 100% | [9 empty] | ü |  |  |  | Completed | 300000 | 0.3601% | 100%
5 | Rehabilitation of Union-Bogak-Rajah Cabungsuan Road (13.5km) | Lingig | 5000000 | ü | ü |  | 100% | [9 empty] | ü |  |  |  | Completed | 5000000 | 6.002% | 100%
6 | Road Opening of 5km Barangay proper to Camuhunan, Bayogo | Madrid | 7500000 | ü | ü | ü | 0% | [13 empty] | On-going | 0 | 0% | 0%
7 | Construction of 10LM Single Lane Flat Slab Bridge at Barangay Bayogo | Madrid | 5000000 | ü | ü |  | 0% | [13 empty] | On-going | 0 | 0% | 0%
8 | Construction of Carromata to Bitaugan Road Opening | San Miguel | 20000000 | ü | ü |  | 0% | [13 empty] | subject to RTWG Validation | 0 | 0% | 0%
9 | Rehabilitation of 8km Poblacion-Batunan Road | Tagbina | 8000000 | ü | ü | ü | 100% | [9 empty] | ü | ü |  |  | On-going | 8000000 | 9.604% | 100%
| TOTAL |  | 83300000 | TOTAL ACCOMPLISHMENT: |  |  | 32.56% | [14 empty] | 30123200 | 32.56% | 32.56%
[6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[6 empty] | 78% | 78% | 78% | 78% | 78% | 78% | 78% | 78% | 78% | 78% | 78%
ON-GOING
COMPLETED
SUSPENDED

## FINANCIAL
PROJECT ALLOCATIONS, CONTRACT COSTS, VARIATIONS AND BALANCES
PAYAPA AT MASAGANG PAMAYANAN (PAMANA)
2012 DILG FUND - REGION XIII
REPORT AS OF: JULY 22, 2013
NO. | LGU/SUB-PROJECT NAME | LOCATION | CONTRACTOR | PROJECT ALLOCATION | ORIGINAL CONTRACT COST | VARIATIONS | LATEST CONTRACT COST | RELEASES |  |  | TARGET VARIANCE | ACTUAL BALANCE | LIQUIDATION |  | PRESENT STATUS | REMARKS
[8 empty] | FIRST TRANCHE | SECOND TRANCHE | TOTAL RELEASE |  |  | LIQUIDATED | UNLIQUIDATED
|  |  |  | (1) | (2) | (3) | (4) = (2) ± (3) | (5) | (6) | (7) = (5) + (6) | (8) = (1) - (4) | (9) = (1) - (7) | (10) | (11) = (7) - (10)
PROJECT YEAR 2012
AGUSAN DEL NORTE
1 | Rehabilitation of Bangonay-NRJ-Inayao-Palo 12 Farm to Market Road | Jabonga | R.B. Candare Construction | 2000000 | 1979145.42 | 0 | 1979145.42 | 1600000 | 379145.42 | 1979145.42 | 20854.58 | 20854.58 | 1880188.15 | 98957.27 | Completed |  | 280188.15
2 | Concreting of San Isidro Farm to Market Road | Las Nieves | Joselle Construction | 1500000 | 1470795.2 | 0 | 1470795.2 | 1200000 | 270795.2 | 1470795.2 | 29204.8 | 29204.8 | 1176636.16 | 294159.04 | On-going |  | -23363.84
3 | Concreting of E.G. Montilla Farm to Market Road | Las Nieves | Joselle Construction | 500000 | 486466.36 | 0 | 486466.36 | 400000 | 86466.36 | 486466.36 | 13533.64 | 13533.64 | 389173.09 | 97293.27 | On-going |  | -10826.91
4 | Concreting Taod-oy Farm to Market Road | Magallanes | LVRO Const. and Supply | 1800000 | 1774225.77 | 0 | 1774225.77 | 1440000 | 334225.77 | 1774225.77 | 25774.23 | 25774.23 | 532267.73 | 1241958.04 | On-going |  | -907732.27
5 | Installation of Potable Water Supply System Level II at Barangay Taod-oy | Magallanes | By Administration | 200000 | 199999.23 | 0 | 199999.23 | 160000 |  | 160000 | 0.77 | 40000 | 158933 | 1067 | On-going |  | -1067
6 | Repair/Rehabilitation of River Flood Control (Armoc Rock Filling) | Tubay | Joselle Construction | 2000000 | 1950132 | 0 | 1950132 | 1600000 | 350132 | 1950132 | 49868 | 49868 | 1852625.4 | 97506.6 | Completed |  | 252625.4
7 | Concreting of Abilan Farm to Market Road | Buenavista | Reyrose Const. and Supply | 2000000 | 1963711.02 | 0 | 1963711.02 | 1600000 | 363711.02 | 1963711.02 | 36288.98 | 36288.98 | 1570990.44 | 392720.58 | Completed |  | -29009.56
8 | Rehabilitation of Manoligao-Liongan Farm to Market Road, Phase 1 | Carmen | ADSE Enterprises | 1000000 | 975997.94 | 0 | 975997.94 | 800000 |  | 800000 | 24002.06 | 200000 |  | 800000 | Just Resumed |  | -800000
9 | Rehabilitation of Poblacion-Sisiman Farm to Market Road | Carmen | ADSE Enterprises | 1000000 | 980649.79 | 0 | 980649.79 | 800000 | 180649.79 | 980649.79 | 19350.21 | 19350.21 | 784519.83 | 196129.96 | Completed |  | -15480.17
10 | Upgrading of Bangayan-Zapanta Valley Farm to Market Road | Kitcharao | BN Builders & Construction Supplies | 2000000 | 1950740.25 | 0 | 1950740.25 | 1600000 | 350740.25 | 1950740.25 | 49259.75 | 49259.75 | 975370.13 | 975370.12 | Completed |  | -624629.87
11 | Concreting of Jaguimitan Farm to Market Road | Nasipit | BN Builders & Construction Supplies | 2000000 | 1955808.15 | 0 | 1955808.15 | 1600000 |  | 1600000 | 44191.85 | 400000 | 1564665.96 | 35334.04 | On-going |  | -35334.04
12 | Construction of Tagbongabong-Kanluran-San Antonio FMR | RTR | Rostel Construction and Supply | 2000000 | 1953743.55 | 0 | 1953743.55 | 1600000 |  | 1600000 | 46256.45 | 400000 | 976871.78 | 623128.22 | On-going |  | -623128.22
13 | Construction of Pob 1-Pangaylan IP-Mantingue Farm to Mantigue | Santiago | ADSE Enterprises | 2000000 | 1955074.52 | 0 | 1955074.52 | 1600000 | 355074.52 | 1955074.52 | 44925.48 | 44925.48 | 1955074.52 | 0 | Completed |  | 355074.52
| TOTAL |  |  | 20000000 | 19596489.2 | 0 | 19596489.2 | 16000000 | 2670940.33 | 18670940.33 | 403510.8 | 1329059.67 | 13817316.19 | 4853624.14
| AGUSAN DEL SUR | [8 empty] | 0 | 0 | 0
1 | Rehabilitation of NRJ San Juan-New Tubigon-San Roque Road | Sibagat | A.T. Dumlao Construction, Inc. | 10000000 | 9767742.08 | 0 | 9767742.08 | 8000000 |  | 8000000 | 232257.92 | 2000000 |  | 8000000 | Just Started
2 | Rehabilitation of La Purisima-Sitio Gacub Road | Prosperidad | LM Construction & Gen. Marketing | 10000000 | 9767074.45 | 225556.87 | 9992631.32 | 8000000 |  | 8000000 | 7368.68 | 2000000 | 7821654.51 | 178345.49 | Completed on original Contract. On-going on variation
3 | Rehabilitation of Tapaz-Tagumpay-Guinobatan Road | Sta. Josefa | ADFIL Corporation | 25000000 | 24338293.13 | -114.97 | 24338178.16 | 20000000 |  | 20000000 | 661821.84 | 5000000 | 12989451.16 | 7010548.84 | Just Started
4 | Rehabilitation of Katipunan-Limot-Anitap-Sisimon Road | Veruela | LM Construction & Gen. Marketing | 25000000 | 24395156.76 | -0.19 | 24395156.57 | 20000000 |  | 20000000 | 604843.43 | 5000000 | 18083229.57 | 1916770.43 | On-going
| TOTAL |  |  | 70000000 | 68268266.42 | 225441.71 | 68493708.13 | 56000000 | 0 | 56000000 | 1506291.87 | 14000000 | 38894335.24 | 17105664.76
SURIGAO DEL NORTE
1 | Rehabilitation of Mainit-Matin-ao-Binga-Paco Road Phase 1 | Mainit | MAMSAR Enterprises | 5000000 | 4943962.55 | 0 | 4943962.55 | 4000000 |  | 4000000 | 56037.45 | 1000000 | 708487.49 | 3291512.51 | On-going
2 | Rehabilitation of Ombong-Camp Edward FMR | Alegria | MAMSAR Enterprises | 4000000 | 3959526.08 | 0 | 3959526.08 | 3200000 |  | 3200000 | 40473.92 | 800000 | 567414.23 | 2632585.77 | On-going
3 | Construction of Water System at Barangay Villariza | Malimono |  | 500000 |  | 0 | 0 | 400000 |  | 400000 |  | 100000 |  | 400000 | For rebidding
4 | Construction of Water System at Barangay Can-aga | Malimono |  | 1000000 |  | 0 | 0 | 800000 |  | 800000 |  | 200000 |  | 800000 | For rebidding
5 | Construction of Water System at Barangay Masgad | Malimono |  | 3000000 |  | 0 | 0 | 2400000 |  | 2400000 |  | 600000 |  | 2400000 | For rebidding
6 | Construction of FMR in Pili-Karihatag Phase I | Malimono | SOCOR Construction Corporation | 5000000 | 4970069.93 | 0 | 4970069.93 | 4000000 |  | 4000000 | 29930.07 | 1000000 |  | 4000000 | On-going
7 | Abaca Development at Barangay Ferlda | Alegria |  | 1000000 |  | 0 | 0 | 800000 |  | 800000 |  | 200000 |  | 800000 | Not yet started
8 | Rehabilitation of FMR at Sitio Pinaypayan-Brazil, Barangay Mat-i | Surigao City |  | 4500000 | 4427666 | 0 | 4427666 | 3600000 |  | 3600000 | 72334 | 900000 |  | 3600000 | Just started
9 | Livelihood Program in Barangay Mat-I, Surigao City | Surigao City |  | 500000 |  | 0 | 0 | 400000 |  | 400000 |  | 100000 | 192900 | 207100 | For procurment
10 | Integrated High Value Crops Production and Mangrove Protection with Livelihood | Siargao Islands |  | 5500000 |  | 0 | 0 | 4400000 |  | 4400000 |  | 1100000 |  | 4400000 | For procurement
| TOTAL |  |  | 30000000 | 18301224.56 | 0 | 18301224.56 | 24000000 |  | 24000000 | 198775.44 | 6000000 | 1468801.72 | 22531198.28
SURIGAO DEL SUR
1 | Rehabilitation and Repair of Poblacion-Magsaysay-Osmena-Villaverde FMR | Tagbina | Christrian Ley Construction | 13500000 | 13439776.88 | 0 | 13439776.88 | 10800000 | 2639776.88 | 13439776.88 | 60223.12 | 60223.12 | 10800000 | 2639776.88 | Completed | Project completed and totally liquidated
2 | Rehabilitation and Repair of Manlambing-Carpenito-Kahayagan FMR | Tagbina | Killusang Magkaibigan MPC | 9000000 | 8955134.27 | -26247.18 | 8928887.09 | 7200000 | 1728887.09 | 8928887.09 | 71112.91 | 71112.91 | 8928887.09 | 0 | Completed | Project completed and totally liquidated
3 | Rehabilitation and Repair of San Isidro-Maticdum-Mabuhay FMR | Tandag | Rowie's Construction | 6500000 | 6464902.4 | 0 | 6464902.4 | 5200000 | 1264902.4 | 6464902.4 | 35097.6 | 35097.6 | 6464902.4 | 0 | Completed | Project completed and totally liquidated
4 | Installation of Potable Water System Level II at Barangay Maligaya | Hinatuan | Han Jin D & B Co. | 3000000 | 2397648 | 137080 | 2534728 | 2400000 | 134728 | 2534728 | 465272 | 465272 | 2393488 | 141240 | Completed
5 | Installation of Potable Water System Level II at Barangay San Antonio | Bislig City | Killusang Magkaibigan MPC | 2500000 | 2470001.02 | 0 | 2470001.02 | 2000000 |  | 2000000 | 29998.98 | 500000 | 1752999.9 | 247000.1 | Completed
6 | Rubber Based Production System at Sito Hapnit, Brgy. San Pedro (Livelihood) | Marihatag | ADC Agricultural Enterprises | 2000000 | 1984438 | 0 | 1984438 | 1600000 |  | 1600000 | 15562 | 400000 | 856045 | 743955 | On-going
7 | Rubber Based Production System at Sitio Tagaraet, Brgy. Panaosawon (Livelihood) | Bayabas | ADC Agricultural Enterprises | 1200000 | 1189988 | 0 | 1189988 | 960000 |  | 960000 | 10012 | 240000 | 454745 | 505255 | On-going
8 | Value Adding Activities for Abaca Weaving Project at Brgy. Pong-on and Janipaan | San Agustin | MOA with DTI SDS | 300000 | 300000 | 0 | 300000 | 240000 |  | 240000 | 0 | 60000 | 240000 | 0 | On-going
| TOTAL |  |  | 38000000 | 37201888.57 | 110832.82 | 37312721.39 | 30400000 | 5768294.37 | 36168294.37 | 687278.61 | 1831705.63 | 31891067.39 | 4277226.98
PROJECT YEAR 2013
| AGUSAN DEL NORTE | [8 empty] | 0 | 0 | 0
1 | Construction of Cabadbaran-Putting Bato-Lanuza Road (Phase 1) | Cabadbaran |  | 5000000 |  |  |  | 4000000 |  | 4000000 | 5000000 | 1000000 |  | 4000000
| TOTAL |  |  | 5000000 | 0 | 0 | 0 | 4000000 | 0 | 4000000 | 5000000 | 1000000 | 0 | 4000000
| SURIGAO DEL NORTE | [8 empty] | 0 | 0 | 0
1 | Construction of Campo-Little Baguio Road, Bacuag (7km) | Bacuag | MAMSAR Enterprises | 30000000 | 28800968.8 | 1118654.91 | 29919623.71 | 23113975.75 |  | 23113975.75 | 80376.29 | 6886024.25 | 15426557.98 | 7687417.77 | On-going
2 | Rehabilitation of Pili-Karihatag Road Phase II, Malimono (2.38km) | Malimono | SOCOR Construction Corporation | 15000000 | 14254872.9 |  | 14254872.9 | 11470814.4 |  | 11470814.4 | 745127.1 | 3529185.6 |  | 11470814.4 | On-going
3 | Rehabilitation of Pinaypayan-Brazil Road, Mat-I Surigao City (0.96km) | Surigao City | SOCOR Construction Corporation | 10000000 | 9551749.2 |  | 9551749.2 | 7716467.48 |  | 7716467.48 | 448250.8 | 2283532.52 |  | 7716467.48 | On-going
4 | Rehabilitation of Cantapoy-Villariza, Malimono (1.22km) | Malimono |  | 10000000 | 9645253.88 |  | 9645253.88 | 7720297.78 |  | 7720297.78 | 354746.12 | 2279702.22 |  | 7720297.78 | Just started
5 | Rehabilitation of Diaz-Magtangale, San Francisco (3.19km) | San Francisco | SOCOR Construction Corporation | 15000000 | 14384505.1 |  | 14384505.1 | 11582050.71 |  | 11582050.71 | 615494.9 | 3417949.29 |  | 11582050.71 | On-going
6 | Construction of 50 meter Bailey Bridge at Cantugas, Mainit (50m) | Mainit |  | 15000000 | 14790292.04 |  | 14790292.04 | 11909982.37 |  | 11909982.37 | 209707.96 | 3090017.63 | 11401692.42 | 508289.95 | Just Started
7 | Construction of Banban-Taganaan-Magsaysay, Placer Road (1.7km) | Tagana-an and Placer |  | 10000000 | 9795216.14 |  | 9795216.14 | 7873578.02 |  | 7873578.02 | 204783.86 | 2126421.98 |  | 7873578.02 | Just Started
8 | Rehabilitation of Antipolo-Tuburan-Quezon, Del Carmen (8.93km) | Del Carmen |  | 30000000 |  |  | 0 | 23684234.96 |  | 23684234.96 |  | 6315765.04 | 4210693.96 | 19473541 | Suspended
| TOTAL |  |  | 135000000 | 101222858.06 | 1118654.91 | 102341512.97 | 105071401.47 | 0 | 105071401.47 | 2658487.03 | 29928598.53 | 31038944.36 | 74032457.11
| SURIGAO DEL SUR | [8 empty] | 0 | 0 | 0
1 | Rehabilitation of Sitio Sote, Burboanan to Junction Mabug, San Roque Road (6km) | Bislig City |  | 2500000 | 2475127.5 | 0 | 2475127.5 | 2000000 | 500000 | 2500000 | 24872.5 | 0 | 2000000 | 500000 | Project just started on July 19, 2013
2 | Concreting of Maticdum-Mabuhay Road, Maticdum, Tandag City | Tandag City |  | 20000000 |  | 0 | 0 | 16000000 |  | 16000000 |  | 4000000 |  | 16000000 | Still on procurement stage | For bidding
3 | Rehabilitation of Mabahin Spring Development, 7km | Cortes (PACKAGE 1) |  | 9000000 | 8954849.84 | 0 | 8954849.84 | 7200000 |  | 7200000 | 45150.16 | 1800000 | 7200000 | 0 | Project just started on July 19, 2013
Rehabilitation of Matho Spring Development 5km
Rehabilitation of Burgos Spring Development
| Rehabilitation of Tigao Spring Development 4km | Cortes (PACKAGE 2) |  | 6300000 | 6256972.93 | 0 | 6256972.93 | 5040000 |  | 5040000 | 43027.07 | 1260000 |  | 5040000 | Project just started on July 19, 2013
Rehabitation of Manlico to Poblacion, 10 km
4 | Construction of Water System Level I (Boac na Bato)
5 | Rehabilitation of Union-Bogak-Rajah Cabungsuan Road (13.5km) | Lingig |  | 5000000 |  | 0 | 0 | 4000000 |  | 4000000 |  | 1000000 |  | 4000000 | Still on procurement stage | For bidding
6 | Road Opening of 5km Barangay proper to Camuhunan, Bayogo | Madrid |  | 7500000 | 7444933.95 | 0 | 7444933.95 | 6000000 |  | 6000000 | 55066.05 | 1500000 |  | 6000000 | Project just started on July 19, 2013
7 | Construction of 10LM Single Lane Flat Slab Bridge at Barangay Bayogo | Madrid |  | 5000000 |  | 0 | 0 | 4000000 |  | 4000000 |  | 1000000 |  | 4000000 | Still on procurement stage | For bidding
8 | Construction of Carromata to Bitaugan Road Opening | San Miguel |  | 20000000 |  | 0 | 0 | 16000000 |  | 16000000 |  | 4000000 |  | 16000000 | Subject to RTWG inspection | For bidding
9 | Rehabilitation of 8km Poblacion-Batunan Road | Tagbina |  | 8000000 | 7940029.65 | 0 | 7940029.65 | 6400000 |  | 6400000 | 59970.35 | 1600000 | 6400000 | 0 | Project just started on July 19, 2013
| TOTAL |  |  | 83300000 | 33071913.87 | 0 | 33071913.87 | 66640000 | 500000 | 67140000 | 228086.13 | 16160000 | 15600000 | 51540000
| Prepared by: | [6 empty] | Reviewed and concurred: | [6 empty] | Noted:
NEIL B. BELUAN
Engineer
Note on L6: VARIANCE: This is the savings generated from the difference of the allocation against contract cost. This savings would be the allowance for possible variation.
Note on M6: BALANCE: This is the amount still not release to or withhold from the LGU based on allocation.
Note on G27: dilgrpoc1: first variation
Note on G28: TAPAZ-TAGUMPAY-GUINOBATAN: FIRST VARIATION Deductive=5,281,735.35 Additive=5,281,620.37 Difference=-114.97
Note on G29: KATIPUNAN-LIMOT-SISIMON FIRST VARIATION additive=3,289,690.91 deductive=3,289,691.1 difference=-0.19
Note on N32: dilgrpoc1: 15% Mobilization: P 708,487.49
Note on N33: dilgrpoc1: 15% Mobilization: 567,414.23
Note on N46: dilgrpoc1: one payment only 100%. The 1,264,902.40 was borrowed and returned to Villaverde FMR
Note on N47: maligaya pws: partial payment only
Note on N58: dilgrpoc1: 15% Mobilization: P 4,320,145.32
Note on N65: dilgrpoc1: 15% Mobilization = 4,210,693.96

## PHYSICAL
TARGET COMPLETION DATES OF PROJECTS
PAYAPA AT MASAGANG PAMAYANAN (PAMANA)
DILG FUND - REGION XIII
NO. | LGU/SUB-PROJECT NAME | LOCATION | PROJECT ALLOCATION | STATUS |  |  |  | ORIGINAL TARGET COMPLETION DATE | NO. OF DAY OF SUSPENSION | NO. OF DAY OF EXTENSION | NEW TARGET COMPLETION DATE | PRESENT STATUS | WOULD THE PROJECT BE COMPLETED ON OR BEFORE NOVEMBER 2013? |  | RECOMMENDATUION / COURSES OF ACTION
|  |  |  | PHYSICAL |  | FINANCIAL
|  |  |  | TARGET | ACTUAL | TARGET | ACTUAL | [5 empty] | YES | NO
PROJECT YEAR 2012
AGUSAN DEL NORTE
1 | Rehabilitation of Bangonay-NRJ-Inayao-Palo 12 Farm to Market Road | Jabonga | 2000000 |  | 100% |  | 2000000 | 2013-03-26 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
2 | Concreting of San Isidro Farm to Market Road | Las Nieves | 1500000 |  | 100% |  | 1500000 | 2013-04-14 |  |  | 2013-06-26 | Completed | ü |  | Closely monitor the project.
3 | Concreting of E.G. Montilla Farm to Market Road | Las Nieves | 500000 |  | 100% |  | 500000 | 2013-03-29 |  |  | 2013-06-09 | Completed | ü |  | Closely monitor the project.
4 | Concreting Taod-oy Farm to Market Road | Magallanes | 1800000 |  | 100% |  | 1800000 | 2013-05-06 |  |  | 2013-07-06 | Completed | ü |  | Closely monitor the project.
5 | Installation of Potable Water Supply System Level II at Brgy Taod-oy | Magallanes | 200000 |  | 100% |  | 200000 | 2013-08-30 |  |  |  | Completed | ü |  | Closely monitor the project.
6 | Repair/Rehabilitation of River Flood Control (Armoc Rock Filling) | Tubay | 2000000 |  | 100% |  | 2000000 | 2013-03-11 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
7 | Concreting of Abilan Farm to Market Road | Buenavista | 2000000 |  | 100% |  | 2000000 | 2013-04-16 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
8 | Rehabilitation of Manoligao-Liongan Farm to Market Road, Phase 1 | Carmen | 1000000 |  | 100% |  | 1000000 | 2013-04-06 |  |  |  | Just Resumed | ü |  | Just resume from suspension due to peace and order situation. Closely monitor the project.
9 | Rehabilitation of Poblacion-Sisiman Farm to Market Road | Carmen | 1000000 |  | 100% |  | 1000000 | 2013-06-02 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
10 | Upgrading of Bangayan-Zapanta Valley Farm to Market Road | Kitcharao | 2000000 |  | 100% |  | 2000000 | 2013-04-05 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
11 | Concreting of Jaguimitan Farm to Market Road | Nasipit | 2000000 |  | 100% |  | 2000000 | 2013-05-18 |  |  | 2013-06-03 | On-going | ü |  | Closely monitor the project.
12 | Construction of Tagbongabong-Kanluran-San Antonio FMR | RTR | 2000000 |  | 73.28% |  | 1465600 | 2013-06-07 |  |  | 2013-07-26 | On-going | ü |  | Closely monitor the project.
13 | Construction of Pob 1-Pangaylan IP-Mantingue Farm to Mantigue | Santiago | 2000000 |  | 100% |  | 2000000 | 2013-05-05 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
| TOTAL |  | 20000000
AGUSAN DEL SUR
1 | Rehabilitation of NRJ San Juan-New Tubigon-San Roque Road | Sibagat | 10000000 |  | 30.37% |  | 3037000 | 2013-11-22 |  |  |  | Just Started | ü |  | Closely monitor the project.
2 | Rehabilitation of La Purisima-Sitio Gacub Road | Prosperidad | 10000000 |  | 100% |  | 10000000 | 2013-06-30 |  | 15 | 2013-07-15 | On-going | ü |  | Closely monitor the project.
3 | Rehabilitation of Tapaz-Tagumpay-Guinobatan Road | Sta. Josefa | 25000000 |  | 98.81% |  | 24702500 | 2014-01-25 |  |  |  | On-going |  | ü | Project was suspended due to rerouting and reprogram after being damaged by Typhoon Pabloo. DILG to communicate LGU to fast-track the implementation. Alert Mechanism to be applied
4 | Rehabilitation of Katipunan-Limot-Sisimon-Anitap Road | Veruela | 25000000 |  | 100% |  | 25000000 | 2013-08-29 |  |  |  | On-going | ü |  | Closely monitor the project.
| TOTAL |  | 70000000
SURIGAO DEL NORTE
1 | Rehabilitation of Mainit-Matin-ao-Binga-Paco Road Phase 1 | Mainit | 5000000 |  | 88.5% |  | 4425000 | 2013-07-23 | 30 | 45 | 2013-10-06 | On-going | ü |  | Closely monitor the project.
2 | Rehabilitation of Ombong-Camp Edward FMR | Alegria | 4000000 |  | 100% |  | 4000000 | 2013-07-23 | 30 |  | 2013-08-22 | On-going | ü |  | Closely monitor the project.
3 | Construction of Water System at Barangay Villariza | Malimono | 500000 |  | 0% |  | 0 |  |  |  | 0 | For rebidding |  | ü | First bidding has failed. DILG to communicate with LGU to fast-track the implementation and do catch-up plan.Closely monitor the project. Alert mechanism to be applied.
4 | Construction of Water System at Barangay Can-aga | Malimono | 1000000 |  | 0% |  | 0 |  |  |  | 0 |  |  | ü
5 | Construction of Water System at Barangay Masgad | Malimono | 3000000 |  | 0% |  | 0 |  |  |  | 0 |  |  | ü
6 | Construction of FMR in Pili-Karihatag | Malimono | 5000000 |  | 44.53% |  | 2226500 | 2013-07-23 |  | 45 | 2013-09-06 | On-going | ü |  | Closely monitor the project.
7 | Abaca Development at Barangay Ferlda | Alegria | 1000000 |  | 0% |  | 0 |  |  |  | 0 | Not yet started |  | ü | Still finalizing the procurment stage. DILG to communicate with LGU to fast-track the implementation and do catch-up plan. Alert mechanism to be applied
8 | Rehabilitation of FMR at Sitio Pinaypayan-Brazil, Barangay Mat-i | Surigao City | 4500000 |  | 47.19% |  | 2123550 | 2013-09-12 |  |  | 2013-09-12 | Just started | ü |  | Closely monitor the project.
9 | Livelihood Program in Barangay Mat-I, Surigao City | Surigao City | 500000 |  | 0% |  | 0 |  |  |  | 0 | For procurment | ü |  | Closely monitor the project.
10 | Integrated High Value Crops Production and Mangrove Protection with Livelihood | Siargao Islands | 5500000 |  | 0% |  | 0 |  |  |  | 0 | For procurement | ü |  | Closely monitor the project.
| TOTAL |  | 30000000 |  |  |  | 0
SURIGAO DEL SUR
1 | Rehabilitation and Repair of Poblacion-Magsaysay-Osmena-Villaverde FMR | Tagbina | 13500000 |  | 100% |  | 13500000 | 2013-06-19 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
2 | Rehabilitation and Repair of Manlambing-Carpenito-Kahayagan FMR | Tagbina | 9000000 |  | 100% |  | 9000000 | 2013-06-26 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
3 | Rehabilitation and Repair of San Isidro-Maticdum-Mabuhay FMR | Tandag | 6500000 |  | 100% |  | 6500000 |  |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
4 | Installation of Potable Water System Level II at Barangay Maligaya | Hinatuan | 3000000 |  | 100% |  | 3000000 | 2013-04-27 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
5 | Installation of Potable Water System Level II at Barangay San Antonio | Bislig City | 2500000 |  | 100% |  | 2500000 | 2013-05-27 |  |  |  | Completed |  |  | DILG to ask Final Liquidation of the project.
6 | Rubber Based Production System at Barangay San Pedro (Livelihood) | Marihatag | 2000000 |  | 89% |  | 1780000 | 2013-07-02 |  |  |  | On-going | ü |  | Closely monitor the project.
7 | Rubber Based Production System at Barangay Panaosawon (Livelihood) | Bayabas | 1200000 |  | 90% |  |  | 2013-07-02 |  |  |  | On-going | ü |  | Closely monitor the project.
8 | Value Adding Activities for Abaca Weaving Project at Brgy. Pong-on and Janipaan | San Agustin | 300000 |  | 80% |  | 240000 | 2013-08-30 |  |  |  | On-going | ü |  | Closely monitor the project.
| TOTAL |  | 38000000 |  |  |  | 36520000
PROJECT YEAR 2013
AGUSAN DEL NORTE
1 | Construction of Cabadbaran-Putting Bato-Lanuza Road (Phase 1) | Cabadbaran | 5000000 |  | 0% | [8 empty] | ü | Almost complete with the project proposal satge. DILG to communicate with LGU to fast track implementation and do catch up plan. Alert Mechanism to be applied.
| TOTAL |  | 5000000
SURIGAO DEL NORTE
1 | Construction of Campo-Little Baguio Road, Bacuag (7km) | Bacuag | 30000000 |  | 86.08% |  | 25824000 | 2013-10-22 | 30 |  | 2013-11-21 | On-going | ü |  | Closely monitor the project.
2 | Rehabilitation of Pili-Karihatag Road, Malimono (2.38km) | Malimono | 15000000 |  | 56.56% |  | 8484000 | 2013-10-12 | 18 |  | 2013-10-30 | On-going | ü |  | Closely monitor the project.
3 | Rehabilitation of Pinaypayan-Brazil Road, Mat-I Surigao City (0.96km) | Surigao City | 10000000 |  | #REF! |  | #REF! | 2013-10-12 |  |  | 2013-10-12 | On-going | ü |  | Closely monitor the project.
4 | Rehabilitation of Cantapoy-Villariza, Malimono (1.22km) | Malimono | 10000000 |  | 25% |  | 2500000 | 2013-10-12 | 69 |  | 2013-12-20 | Just started | ü |  | Closely monitor the project.
5 | Rehabilitation of Diaz-Magtangale, San Francisco (3.19km) | San Francisco | 15000000 |  | #REF! |  | #REF! | 2013-10-12 |  |  | 2013-10-12 | On-going | ü |  | Closely monitor the project.
6 | Construction of 50 meter Bailey Bridge at Cantugas, Mainit (50m) | Mainit | 15000000 |  | 71.2% |  | 10680000 | 2013-10-12 |  |  | 2013-10-12 | Just Started | ü |  | Closely monitor the project.
7 | Construction of Banban-Taganaan-Magsaysay, Placer Road (1.7km) | Tagana-an and Placer | 10000000 |  | #REF! |  | #REF! | 2013-09-27 |  |  | 2013-09-27 | Just Started | ü |  | Closely monitor the project.
8 | Rehabilitation of Antipolo-Tuburan-Quezon, Del Carmen (8.93km) | Del Carmen | 30000000 |  | 0% |  | 0 | 2013-12-27 |  |  | 2013-12-27 | On-going |  | ü | RTWG just reconsidered the first proposal of the LGU for a graveled road. Construction will take off ASAP. DILG to communicate with LGU to make catch-up plan.
| TOTAL |  | 135000000
SURIGAO DEL SUR
1 | Rehabilitation of Sitio Sote, Burboanan to Junction Mabug, San Roque Road (6km) | Bislig City | 2500000 |  | 100% |  | 0 | 2013-10-09 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
2 | Concreting of Maticdum-Mabuhay Road, Maticdum, Tandag City | Tandag City | 20000000 |  | 0% |  | 0 |  |  |  |  | Still on procurement stage | ü |  | Closely monitor the project. | 2013-07-19
3 | Rehabilitation of Mabahin Spring Development, 7km | Cortes | 15000000 |  | 100% |  | 0 | 2013-11-08 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
| Rehabilitation of Matho Spring Development 5km |  |  |  | 100% |  | 0 | 2013-11-08 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
| Rehabilitation of Tigao Spring Development 4km |  |  |  | 100% |  | 0 | 2013-11-08 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
| Rehabitation of Manlico to Poblacion, 10 km |  |  |  | 77.44% |  | 0 | 2013-11-08 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
4 | Construction of Water System Level I (Boac na Bato) | Cortes | 300000 |  | 100% |  | 0 | 2013-11-08 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
5 | Rehabilitation of Union-Bogak-Rajah Cabungsuan Road (13.5km) | Lingig | 5000000 |  | 100% |  | 0 |  |  |  |  | Still on procurement stage | ü |  | Closely monitor the project. | 2013-07-19
6 | Road Opening of 5km Barangay proper to Camuhunan, Bayogo | Madrid | 7500000 |  | 0% |  | 0 | 2013-10-09 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
7 | Construction of 10LM Single Lane Flat Slab Bridge at Barangay Bayogo | Madrid | 5000000 |  | 0% |  | 0 | 2013-10-13 |  |  |  | Still on procurement stage | ü |  | Closely monitor the project. | 2013-07-19
8 | Construction of Carromata to Bitaugan Road Opening | San Miguel | 20000000 |  | 0% |  | 0 |  |  |  |  | Suspended |  | ü | Project cannot start until the adjacent road under other fund will be completed. LGU commited to complete the this first section by August 30, 2013, so that the DILG-Fund could start afterwards. DILG RO withheld the release of the fund until LGU is ready to start the project.
9 | Rehabilitation of 8km Poblacion-Batunan Road | Tagbina | 8000000 |  | 100% |  | 0 | 2013-10-09 |  |  |  | Project just started on July 19, 2013 | ü |  | Closely monitor the project. | 2013-07-19
| TOTAL |  | 83300000
| Prepared by: |  |  | Reviewed and concurred: | [7 empty] | Noted:
| NEIL B. BELUAN |  |  |  | ANNABELLE IVY R. BOQUIREN | [7 empty] | LILIBETH A. FAMACION, CESO IV
| Engineer |  |  |  | PAMANA Regional Focal Person | [7 empty] | Regional Director
Formulas:
NEW TARGET COMPLETION DATE = [ORIGINAL TARGET COMPLETION DATE]+[NO. OF DAY OF EXTENSION]
NEW TARGET COMPLETION DATE = [ORIGINAL TARGET COMPLETION DATE]+[NO. OF DAY OF SUSPENSION]+[NO. OF DAY OF EXTENSION]

## liquidation
PAMANA DILG FUND (Region XIII)
REPORT OF FUND RELEASES AND LIQUIDATIONS BY PROJECT IMPLEMENTING UNITS (LGUs)
Project Year: 2012
PROVINCE | Total Allocation | Total Amount Released to LGU for First Tranche | Total Amount Released to LGU for Second Tranche | Total Amount Released to LGU (1st and 2nd Tranche) | Amount Withheld at RO for release subject to submission of doc. requirements by LGU | Total Amount Liquidated by LGU | Percent of Liquidation
Agusan del Norte | 20000000 | 16000000 | 2670940.33 | 18670940.33 | 1329059.67 | 13817316.19 | 74%
Agusan del Sur | 70000000 | 56000000 | 0 | 56000000 | 14000000 | 38894335.24 | 69.45%
Surigao del Norte | 30000000 | 24000000 | 0 | 24000000 | 6000000 | 1468801.72 | 6.12%
Surigao del Sur | 38000000 | 30400000 | 5768294.37 | 36168294.37 | 1831705.63 | 31891067.39 | 88.17%
TOTAL | 158000000 | 126400000 | 8439234.7 | 134839234.7 | 23160765.3 | 86071520.54 | 63.83%
Project Year: 2013
PROVINCE | Total Allocation | Total Amount Released to LGU for First Tranche | Total Amount Released to LGU for Second Tranche | Total Amount Released to LGU (1st and 2nd Tranche) | Amount Withheld at RO for release subject to submission of doc. requirements by LGU | Total Amount Liquidated by LGU | Percent of Liquidation
Agusan del Norte | 5000000 | 4000000 | 0 | 4000000 | 1000000 | 0 | 0%
Surigao del Norte | 135000000 | 105071401.47 | 0 | 105071401.47 | 29928598.53 | 0 | 0%
Surigao del Sur | 83300000 | 66640000 | 500000 | 67140000 | 16160000 | 15600000 | 8.853%
TOTAL | 223300000 | 175711401.47 | 500000 | 176211401.47 | 47088598.53 | 15600000 | 8.853%
Note: Summary of Unliquidated Cash Advances dated September 30, 2013 was already submitted to DILG-Central Office.

## REPORT SUBMITTED
REPORT SUBMITTED
PAYAPA AT MASAGANG PAMAYANAN (PAMANA)
2012-2013 DILG FUND - REGION XIII
NO. | LGU/SUB-PROJECT NAME | LOCATION | PROJECT ALLOCATION | PRESENT STATUS | PFAR SUBMITTED |  |  |  | RECOMMENDATUION / COURSES OF ACTION
[5 empty] | MAY | JUNE | JULY | AUG
PROJECT YEAR 2012
AGUSAN DEL NORTE
1 | Rehabilitation of Bangonay-NRJ-Inayao-Palo 12 Farm to Market Road | Jabonga | 2000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
2 | Concreting of San Isidro Farm to Market Road | Las Nieves | 1500000 | On-going |  |  |  |  | Closely monitor the project.
3 | Concreting of E.G. Montilla Farm to Market Road | Las Nieves | 500000 | On-going |  |  |  |  | Closely monitor the project.
4 | Concreting Taod-oy Farm to Market Road | Magallanes | 1800000 | On-going |  |  |  |  | Closely monitor the project.
5 | Installation of Potable Water Supply System Level II at Barangay Taod-oy | Magallanes | 200000 | On-going |  |  |  |  | Closely monitor the project.
6 | Repair/Rehabilitation of River Flood Control (Armoc Rock Filling) | Tubay | 2000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
7 | Concreting of Abilan Farm to Market Road | Buenavista | 2000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
8 | Rehabilitation of Manoligao-Liongan Farm to Market Road, Phase 1 | Carmen | 1000000 | Just Resumed |  |  |  |  | Just resume from suspension due to peace and order situation. Closely monitor the project.
9 | Rehabilitation of Poblacion-Sisiman Farm to Market Road | Carmen | 1000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
10 | Upgrading of Bangayan-Zapanta Valley Farm to Market Road | Kitcharao | 2000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
11 | Concreting of Jaguimitan Farm to Market Road | Nasipit | 2000000 | On-going |  |  |  |  | Closely monitor the project.
12 | Construction of Tagbongabong-Kanluran-San Antonio FMR | RTR | 2000000 | On-going |  |  |  |  | Closely monitor the project.
13 | Construction of Pob 1-Pangaylan IP-Mantingue Farm to Mantigue | Santiago | 2000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
| TOTAL |  | 20000000
AGUSAN DEL SUR
1 | Rehabilitation of NRJ San Juan-New Tubigon-San Roque Road | Sibagat | 10000000 | Just Started | ü | ü |  |  | Closely monitor the project.
2 | Rehabilitation of La Purisima-Sitio Gacub Road | Prosperidad | 10000000 | On-going | ü | ü |  |  | Closely monitor the project.
3 | Rehabilitation of Tapaz-Tagumpay-Guinobatan Road | Sta. Josefa | 25000000 | Just Started |  |  |  |  | Project was suspended due to rerouting and reprogram after being damaged by Typhoon Pabloo. DILG to communicate LGU to fast-track the implementation. Alert Mechanism to be applied
4 | Rehabilitation of Katipunan-Limot-Sisimon-Anitap Road | Veruela | 25000000 | On-going |  | ü |  |  | Closely monitor the project.
| TOTAL |  | 70000000
SURIGAO DEL NORTE
1 | Rehabilitation of Mainit-Matin-ao-Binga-Paco Road Phase 1 | Mainit | 5000000 | On-going |  |  |  | ü | Closely monitor the project.
2 | Rehabilitation of Ombong-Camp Edward FMR | Alegria | 4000000 | On-going |  |  |  | ü | Closely monitor the project.
3 | Construction of Water System at Barangay Villariza | Malimono | 500000 | For rebidding |  |  |  |  | First bidding has failed. DILG to communicate with LGU to fast-track the implementation and do catch-up plan.Closely monitor the project. Alert mechanism to be applied.
4 | Construction of Water System at Barangay Can-aga | Malimono | 1000000
5 | Construction of Water System at Barangay Masgad | Malimono | 3000000
6 | Construction of FMR in Pili-Karihatag | Malimono | 5000000 | On-going |  |  |  |  | Closely monitor the project.
7 | Abaca Development at Barangay Ferlda | Alegria | 1000000 | Not yet started |  |  |  |  | Still finalizing the procurment stage. DILG to communicate with LGU to fast-track the implementation and do catch-up plan. Alert mechanism to be applied
8 | Rehabilitation of FMR at Sitio Pinaypayan-Brazil, Barangay Mat-i | Surigao City | 4500000 | Just started |  |  |  |  | Closely monitor the project.
9 | Livelihood Program in Barangay Mat-I, Surigao City | Surigao City | 500000 | For procurment |  |  |  |  | Closely monitor the project.
10 | Integrated High Value Crops Production and Mangrove Protection with Livelihood | Siargao Islands | 5500000 | For procurement |  |  |  |  | Closely monitor the project.
| TOTAL |  | 30000000
SURIGAO DEL SUR
1 | Rehabilitation and Repair of Poblacion-Magsaysay-Osmena-Villaverde FMR | Tagbina | 13500000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
2 | Rehabilitation and Repair of Manlambing-Carpenito-Kahayagan FMR | Tagbina | 9000000 | Completed |  |  |  |  | PROJECT COMPLETED AND LIQUIDATED
3 | Rehabilitation and Repair of San Isidro-Maticdum-Mabuhay FMR | Tandag | 6500000 | Completed |  |  |  |  | PROJECT COMPLETED AND LIQUIDATED
4 | Installation of Potable Water System Level II at Barangay Maligaya | Hinatuan | 3000000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
5 | Installation of Potable Water System Level II at Barangay San Antonio | Bislig City | 2500000 | Completed |  |  |  |  | DILG to ask Final Liquidation of the project.
6 | Rubber Based Production System at Barangay San Pedro (Livelihood) | Marihatag | 2000000 | On-going |  |  |  |  | Closely monitor the project.
7 | Rubber Based Production System at Barangay Panaosawon (Livelihood) | Bayabas | 1200000 | On-going |  |  |  |  | Closely monitor the project.
8 | Value Adding Activities for Abaca Weaving Project at Brgy. Pong-on and Janipaan | San Agustin | 300000 | On-going |  |  |  |  | Closely monitor the project.
| TOTAL |  | 38000000
PROJECT YEAR 2013
AGUSAN DEL NORTE
1 | Construction of Cabadbaran-Puting Bato-Lanuza Road (Phase 1) | Cabadbaran | 5000000 | [5 empty] | Almost complete with the project proposal satge. DILG to communicate with LGU to fast track implementation and do catch up plan. Alert Mechanism to be applied.
| TOTAL |  | 5000000
SURIGAO DEL NORTE
1 | Construction of Campo-Little Baguio Road, Bacuag (7km) | Bacuag | 30000000 | On-going |  |  |  | ü | Closely monitor the project.
2 | Rehabilitation of Pili-Karihatag Road, Malimono (2.38km) | Malimono | 15000000 | On-going |  |  |  |  | Closely monitor the project.
3 | Rehabilitation of Pinaypayan-Brazil Road, Mat-I Surigao City (0.96km) | Surigao City | 10000000 | On-going |  |  |  |  | Closely monitor the project.
4 | Rehabilitation of Cantapoy-Villariza, Malimono (1.22km) | Malimono | 10000000 | Just started |  |  |  |  | Closely monitor the project.
5 | Rehabilitation of Diaz-Magtangale, San Francisco (3.19km) | San Francisco | 15000000 | On-going |  |  |  |  | Closely monitor the project.
6 | Construction of 50 meter Bailey Bridge at Cantugas, Mainit (50m) | Mainit | 15000000 | Just Started |  |  |  | ü | Closely monitor the project.
7 | Construction of Banban-Taganaan-Magsaysay, Placer Road (1.7km) | Tagana-an and Placer | 10000000 | Just Started |  |  |  | ü | Closely monitor the project.
8 | Rehabilitation of Antipolo-Tuburan-Quezon, Del Carmen (8.93km) | Del Carmen | 30000000 | Suspended |  |  |  |  | RTWG just reconsidered the first proposal of the LGU for a graveled road. Construction will take off ASAP. DILG to communicate with LGU to make catch-up plan.
| TOTAL |  | 135000000
SURIGAO DEL SUR
1 | Rehabilitation of Sitio Sote, Burboanan to Junction Mabug, San Roque Road (6km) | Bislig City | 2500000 | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
2 | Concreting of Maticdum-Mabuhay Road, Maticdum, Tandag City | Tandag City | 20000000 | Still on procurement stage |  |  |  |  | Closely monitor the project. | 2013-07-19
3 | Rehabilitation of Mabahin Spring Development, 7km | Cortes | 15000000 | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
| Rehabilitation of Matho Spring Development 5km |  |  | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
| Rehabilitation of Tigao Spring Development 4km |  |  | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
| Rehabitation of Manlico to Poblacion, 10 km |  |  | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
4 | Construction of Water System Level I (Boac na Bato) | Cortes | 300000 | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
5 | Rehabilitation of Union-Bogak-Rajah Cabungsuan Road (13.5km) | Lingig | 5000000 | Still on procurement stage |  |  |  |  | Closely monitor the project. | 2013-07-19
6 | Road Opening of 5km Barangay proper to Camuhunan, Bayogo | Madrid | 7500000 | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
7 | Construction of 10LM Single Lane Flat Slab Bridge at Barangay Bayogo | Madrid | 5000000 | Still on procurement stage |  |  |  |  | Closely monitor the project. | 2013-07-19
8 | Construction of Carromata to Bitaugan Road Opening | San Miguel | 20000000 | Suspended |  |  |  |  | Project cannot start until the adjacent road under other fund will be completed. LGU commited to complete the this first section by August 30, 2013, so that the DILG-Fund could start afterwards. DILG RO withheld the release of the fund until LGU is ready to start the project.
9 | Rehabilitation of 8km Poblacion-Batunan Road | Tagbina | 8000000 | Project just started on July 19, 2013 |  |  |  |  | Closely monitor the project. | 2013-07-19
| TOTAL |  | 83300000
| Prepared by: |  |  | Noted:
NEIL B. BELUAN
Engineer

## Sheet1
Province:
Project Name | Location | Amount | Status | Issues and Concern | Project Billboard | Community Billboard | Project Validation | Social Preparation
PAMANA GUIDELINES | YES | NO | ISSUES AND CONCERNS
Project Billboard
Project Validation
Social Preparation
C. Orientation to the community
D. Formulation of project sustainability plan